## Data Navigator Issue Follow up
No | Issue Description | CBO Comments | eMcREY Comments | Target Date | Testing Status | Result | Production Deployment Status
1 | Querry Window | 1) If the TXN source is GL : matching status please add
a) CB Match with swtich File
b) CB Match with EJ file
c) CB Match with network (Ethswitch ) file
d) CB Not match with network eth switch ) file
2) If the TXN source is switch: matching status please add
a)Switch Match with EJ fILE
b) Swtich Match with Network (Ethswitchh )
c) Switch Not Match with Network (Eth switch )
3) If the TXN source is Gl and the matching status CB does not match with the Ej file (Ej file Missing ), is there any file available from IST switch as a substitute for the EJ file , since this transaction has a financial impact on the bank
4) If the TXN source is Gl and the matching status CB does not match with the Ej file_add Matching criteria
5) If the TXN source is Gl and the matching status CB does not match with the Ej file_Considering off us transaction (Other bank card _CBO terminal )
2 | Reconcilation Details | 1) The difference amount shall be kept under proper cash shortage and Excess NCR_ATM and CRM account .Please use the attached Terminal account information (A/R _Cash shortage and A/P_Cash Excess account )
a) We need the exact list of transaction for cash shorage /Excess account
b) if the cash shortage _A/R for NCR_ATM/CRM_We need the details Information.We can provide the file format
c) if the cash Excess _A/p for NCR_ATM/CRM_We need the details Information.We can provide the file format

## DN UI Issues
No | Main Menu | Menu | Sub Menu | Functionality | Issues | Result
1 | Configure | Main Configuration | Institution | Remove Institution type | Failed to remove created institution
2 | Configure | Main Configuration | Country | new Country | Failed to record country
3 | Configure | Main Configuration | Card Scheme | new Card Scheme | failed to create new records
4 | Configure | Main Configuration | Currency | new Currency | failed to create new records
5 | Configure | Main Configuration | Currency rates | new Currency rates | failed to create new records
6 | Configure | Main Configuration | Adress | new Address | failed to create new Address
7 | Configure | Main Configuration | Country, Province,county | creating new | failed to create new records
8 | Configure | Main Configuration | Netting Account Configuration | creating new | failed to create new records
9 | Configure | ATM Configuration | ATM model | ATM Type Dropdown | no ATM type Option List even tough there is record at ATM type
10 | Configure | ATM Configuration | ATM Group | New ATM group | failed to create new ATM Group
11 | Configure | ATM Configuration | Branch | New Branch | failed Saving Branch
12 | Stock Management | Vendor | Edit vendor | Add a link and contact address | unable to add link and contact address
13 | Stock Management | Brand | Add New Brand | choose type of brand and and model | unable to create a brand
14 | Stock Management | Device Inventory | New Device Inventory | Choose a drop down option | unable to choose a prefered network Type
15 | Stock Management | Clone Device Inventory |  | Clone device inventory | Unable to clone device inventory
16 | Stock Management | Atm Defination | New Atm Defination | Add a new ATM defination | Unable ATM defination
17 | Stock Management | Atm Defination | New Atm Defination | Export | Exports less number of data
18 | Stock Management | Atm Enquiry | Search | Search an inactive Atm | Unable to show an inactive ATMs
18 | eJournal | Browse Ejournal Transaction | Search | Search an Ej transaction | Unable to search Ej a transaction
19 | Online Monitoring | Inquiry Switch/ GL | Query Window | transaction details | No detail info can be viewed on each specific Transaction
20 | Reconcilation | Query Reconcilation Results | Reconcilation Details | Reject a trasaction | No Appropriate Reason is Displayed
22